## Slide 1
LEDGER SERVICE V3
Migration Readiness Assessment
Northwind Payments · Platform Engineering
PE-RA-2026-014 · Revision C · 21 August 2026
Internal — Confidential
Notes: Twenty-one days of shadow traffic and a full performance soak. The recommendation is a conditional go: three blockers must close by 25 September.

## Slide 2
02 / 13
What this deck covers
Where we are
Performance against objectives
Data integrity
Risks and blockers
Cost and payback
Timeline and recommendation
RECOMMENDATION
Conditional go
Cut over on 12–13 October, once all three blockers are closed and signed off by 25 September 2026.
Notes: Lead with the verdict, then walk the evidence. Sections 2 and 3 are the evidence; 4 to 6 are the ask.

## Slide 3
03 / 13
Twenty-one days, four numbers
+124%
Posting throughput, single entry
1,420 → 3,180 tps
37 ms
p95 on POST /entries
against a 50 ms objective
37
Mismatches in 412,380,551 entries
all of them before 3.0.4
−5.7%
Monthly infrastructure cost
$55,010 → $51,860
Notes: Every figure is the median of three 45-minute soaks on the same hardware, measured at the load generator.

## Slide 4
04 / 13
Latency against objectives
Endpoint | v2.7 p95 | v3.0 p95 | Target | Verdict
POST /entries | 84 ms | 37 ms | ≤ 50 ms | Pass
GET /accounts/{id}/balance | 12 ms | 11 ms | ≤ 25 ms | Pass
POST /reversals | 143 ms | 61 ms | ≤ 100 ms | Pass
GET /statements (90-day range) | 1,910 ms | 2,240 ms | ≤ 1,500 ms | Fail
Blocker B-1. GET /statements over 90 days is 17% slower than v2.7 and misses its objective by 740 ms. A query plan diff traced it to a missing covering index on the new partition scheme. The fix is queued for 3.0.5 and must land before Phase 2.
Notes: Three of four endpoints pass comfortably. The statement endpoint is the only regression, and it has a known cause and a known fix.

## Slide 5
05 / 13
Throughput by workload
Chart: 
| Posting, single entry | Balance read, cold | Reversal
v2.7 baseline | 1420 | 2050 | 880
v3.0 candidate | 3180 | 1780 | 1910
Transactions per second, median of three 45-minute soaks. Batch posting (9,600 → 24,100 tps) and cached balance reads (41,000 → 44,500 tps) are left out so the scale stays readable.
Notes: The cold-read regression is real but expected: the new cache key layout means a flush costs more to recover from. Pre-warming closes most of the gap.

## Slide 6
06 / 13
Three blockers stand between us and cutover.
None is technically hard.
All three are schedule risk.
Section 6 — Recommendations
Notes: This is the ask. Everything before it is evidence; everything after it is the plan for closing these three.

## Slide 7
07 / 13
The three blockers
B-1
Statement endpoint misses its objective
Ship the covering index in 3.0.5 and re-measure under the same soak.
M. Farouk · due 8 September
B-2
Rollback designed but never rehearsed
Rehearse twice against a production-sized dataset and record the wall-clock time.
A. Reyes · due 18 September
B-3
Second game day not yet run
Half the on-call rotation has not used the rewritten runbook without help.
S. Okafor · due 25 September
Notes: Each blocker has one named owner and one dated exit. If B-2 slips past 18 September the cutover moves to the 26 October window.

## Slide 8
08 / 13
Mismatches fell to zero after 3.0.4
Chart: 
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
Mismatched entries per day | 4 | 3 | 5 | 2 | 4 | 3 | 2 | 3 | 2 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37
mismatches in 412,380,551 entries
9.0 × 10⁻⁸ of all entries
All on foreign-exchange legs with six or more decimal places. None affected a settled balance.
3.0.4 shipped on day 14 and removed the double-rounding path. Zero mismatches in the final seven days.
Notes: v2.7 rounded once at persist time. v3.0 rounded in the pricing stage and again at the ledger boundary. Two roundings are not one rounding.

## Slide 9
09 / 13
Risks that gate the cutover
Score is likelihood × impact. Anything at 12 or above needs a named owner and a dated mitigation.
R-02 · score 15
Dual-write drift
Entries diverge while both systems are written to during the cutover window.
Freeze writes for 90 s, reconcile before opening traffic.
A. Reyes
R-04 · score 15
Rollback exceeds RTO
Returning to v2.7 takes longer than the 30-minute recovery objective.
Rehearse twice. Keep v2.7 warm for 14 days.
A. Reyes
R-01 · score 12
Statement SLO miss
The 90-day statement query stays above its 1,500 ms objective.
Covering index in 3.0.5, before Phase 2.
M. Farouk
Notes: R-03, R-05 and R-06 score below 12 and are tracked in the report, not here.

## Slide 10
10 / 13
Cost and payback
Line item | v2.7 / month | v3.0 / month | Change
Compute — API tier | $18,400 | $11,900 | −$6,500
Compute — worker tier | $7,250 | $8,900 | +$1,650
Managed PostgreSQL | $22,000 | $22,000 | $0
Redis cache | $3,100 | $4,400 | +$1,300
Object storage and egress | $1,860 | $1,910 | +$50
Observability | $2,400 | $2,750 | +$350
Total | $55,010 | $51,860 | −$3,150
−$3,150
Saved every month at today's volume
13.0
Months to pay back 6.5 engineer-weeks of migration work
At the 22% volume growth Finance forecasts, the saving widens to about $4,900 a month.
Projected monthly infrastructure cost at current production volume. Volume held constant.
Notes: Payback of 13 months sits inside the platform group's 18-month threshold for infrastructure work.

## Slide 11
11 / 13
How parity was proved
Every live request was copied to v3.0. Its response was thrown away; only the resulting ledger entries were compared.
Twenty-one consecutive days at 100% of production volume. No customer ever saw a v3.0 response.
Shadow topology, September 2026. Diagram rendered from Mermaid source.
Notes: The comparator runs off the two databases, not off the responses, so a v3.0 timeout still gets compared.

## Slide 12
12 / 13
Phased cutover
0
1–11 Sep
Phase 0
Prep, freeze,
index deploy
1
14–25 Sep
Phase 1
Shadow traffic
at 100%
2
28 Sep – 9 Oct
Phase 2
Canary
5% → 25%
3
12–13 Oct
Phase 3
Full cutover
4
27 Oct
Phase 4
Decommission
v2.7
Each phase has a single, testable exit criterion. Phase 2 exists to catch slow-burning divergence, so it is not compressed if an earlier phase slips.
Notes: If B-2 slips past 18 September the whole plan moves to the 26 October maintenance window. Phase 2 is never shortened.

## Slide 13
CONDITIONAL GO
Close B-1, B-2 and B-3 by 25 September 2026, then cut over on 12–13 October.
A. Reyes (lead) · M. Farouk · J. Lindqvist
Prepared for R. Halversen, VP Engineering
Cutover runbook
Notes: Sign-off gate is checked immediately before Phase 3. Three of six items are already green.