## Read me
Ledger Service v3 — Assessment Workbook
Every figure in report PE-RA-2026-014 Rev. C, with the arithmetic left in place.
Document | PE-RA-2026-014 · Revision C
Prepared by | A. Reyes (lead), M. Farouk, J. Lindqvist
Prepared for | R. Halversen, VP Engineering
Date | 2026-08-21
Classification | Internal — Confidential
Sheet | What it holds
Assumptions | Every input the rest of the workbook reads. Blue cells are the only things to edit.
Throughput | Sustained transactions per second by workload, v2.7 against v3.0.
Latency | p95 latency per endpoint against its published objective.
Shadow run | Twenty-one days of entry-by-entry comparison, day by day.
Cost model | Monthly infrastructure cost, the saving, and the payback period.
Risk register | Open risks, scored. Anything at 12 or above gates the cutover.
Readiness | The operational checklist and how much of it is done.
Headline figures
Entries compared | 412380551
Mismatches recorded | 37
Mismatch rate | 8.9723e-08
Saved every month | 3150
Payback period (months) | 13
Risks that gate the cutover | 3
Readiness items complete | 4
Conventions
Blue text | A hard-coded input. Change these and the workbook follows.
Black text | A formula. Do not overwrite it with a number.
Named ranges | MigrationWeeks, CostPerWeek, VolumeGrowth, WarmFleetDays, WarmFleetDailyCost, RiskGateThreshold, EntriesCompared.
Sample workbook. All names, figures and findings are invented.

## Assumptions
Assumptions
Section references point at PE-RA-2026-014 Rev. C. Blue cells are inputs; nothing here is derived.
Parameter | Value | Unit | Source
MigrationWeeks | 6.5 | engineer-weeks | §4
CostPerWeek | 6300 | $ per engineer-week | §4
VolumeGrowth | 22% | fraction, next 12 months | Finance forecast
WarmFleetDays | 14 | days v2.7 stays warm | §6.4
WarmFleetDailyCost | 915 | $ per day | §6.4
RiskGateThreshold | 12 | score that gates cutover | PE-STD-004
ShadowDays | 21 | days of shadow traffic | §2.1
RTOMinutes | 30 | minutes, recovery objective | §5 R-04
EntriesCompared | 412380551 | entries in the shadow run | §3.3
One-time migration cost | 40950 | derived from the two rows above
Cost of keeping v2.7 warm | 12810 | seven days longer than first planned

## Throughput
Throughput by workload
Sustained transactions per second, median of three 45-minute soaks on identical hardware.
Workload | v2.7 baseline | v3.0 candidate | Change | Direction
Posting, single entry | 1420 | 3180 | 123.9% | Faster
Posting, batch of 500 | 9600 | 24100 | 151% | Faster
Balance read, cached | 41000 | 44500 | 8.537% | Faster
Balance read, cold | 2050 | 1780 | -13.17% | Slower
Reversal | 880 | 1910 | 117% | Faster
The cold-read regression follows from the new cache key layout: entries that used to share a key now sit in separate slots, so a flush costs more to recover from. Pre-warming closes most of the gap.

## Latency
Latency against objectives
p95 at peak load, measured at the load generator rather than inside the service.
Endpoint | v2.7 p95 | v3.0 p95 | Objective | Change | Headroom | Verdict
POST /entries | 84 | 37 | 50 | -55.95% | 13 | Pass
GET /accounts/{id}/balance | 12 | 11 | 25 | -8.333% | 14 | Pass
POST /reversals | 143 | 61 | 100 | -57.34% | 39 | Pass
GET /statements (90-day range) | 1910 | 2240 | 1500 | 17.28% | -740 | Fail
Endpoints inside objective | 3 of 4
Worst miss | 740
Blocker B-1. A query plan diff traced the statement regression to a missing covering index on the new partition scheme. The fix is queued for 3.0.5 and must land before Phase 2.

## Shadow run
Shadow run, day by day
Every live request was copied to v3.0 and its response discarded. Only the resulting ledger entries were compared.
Day | Date | Entries compared | Mismatches | Cumulative | Rate to date | Build under test
1 | 2026-07-26 | 15587537 | 4 | 4 | 2.5662e-07 | 3.0.3
2 | 2026-07-27 | 20843372 | 3 | 7 | 1.9214e-07 | 3.0.3
3 | 2026-07-28 | 22332184 | 5 | 12 | 2.0421e-07 | 3.0.3
4 | 2026-07-29 | 20417997 | 2 | 14 | 1.7681e-07 | 3.0.3
5 | 2026-07-30 | 21481434 | 4 | 18 | 1.7882e-07 | 3.0.3
6 | 2026-07-31 | 22544872 | 3 | 21 | 1.7044e-07 | 3.0.3
7 | 2026-08-01 | 14376855 | 2 | 23 | 1.6717e-07 | 3.0.3
8 | 2026-08-02 | 15436202 | 3 | 26 | 1.6991e-07 | 3.0.3
9 | 2026-08-03 | 20630684 | 2 | 28 | 1.6124e-07 | 3.0.3
10 | 2026-08-04 | 22119497 | 3 | 31 | 1.5835e-07 | 3.0.3
11 | 2026-08-05 | 21268747 | 2 | 33 | 1.5205e-07 | 3.0.3
12 | 2026-08-06 | 19992622 | 2 | 35 | 1.4766e-07 | 3.0.3
13 | 2026-08-07 | 21906809 | 1 | 36 | 1.3903e-07 | 3.0.3
14 | 2026-08-08 | 15890208 | 1 | 37 | 1.3463e-07 | 3.0.3 → 3.0.4
15 | 2026-08-09 | 14982196 | 0 | 37 | 1.2767e-07 | 3.0.4
16 | 2026-08-10 | 21694122 | 0 | 37 | 1.1878e-07 | 3.0.4
17 | 2026-08-11 | 20417997 | 0 | 37 | 1.1147e-07 | 3.0.4
18 | 2026-08-12 | 22544872 | 0 | 37 | 1.0438e-07 | 3.0.4
19 | 2026-08-13 | 20843372 | 0 | 37 | 9.8585e-08 | 3.0.4
20 | 2026-08-14 | 21481434 | 0 | 37 | 9.3248e-08 | 3.0.4
21 | 2026-08-15 | 15587538 | 0 | 37 | 8.9723e-08 | 3.0.4
Total |  | 412380551 | 37 |  | 8.9723e-08
Entries expected (Assumptions) |  |  | 412380551
Check |  |  | OK
Mismatches after 3.0.4 shipped |  |  | 0

## Cost model
Cost model
Projected monthly infrastructure cost at current production volume, and what happens when volume grows.
Line item | v2.7 / month | v3.0 / month | Change | Change % | Scales with posting rate
Compute — API tier | 18400 | 11900 | -6500 | -35.33% | Yes
Compute — worker tier | 7250 | 8900 | 1650 | 22.76% | No
Managed PostgreSQL | 22000 | 22000 | 0 | 0% | No
Redis cache | 3100 | 4400 | 1300 | 41.94% | No
Object storage and egress | 1860 | 1910 | 50 | 2.688% | No
Observability | 2400 | 2750 | 350 | 14.58% | No
Total | 55010 | 51860 | -3150 | -5.726%
Payback
Saved every month |  | 3150
Migration effort |  | 6.5
Cost per engineer-week |  | 6300
One-time migration cost |  | 40950
Payback period |  | 13
Cost of keeping v2.7 warm |  | 12810
At the volume Finance forecasts
Volume growth |  | 22%
v2.7 cost at forecast volume |  | 59058
v3.0 cost at forecast volume |  | 54478
Saving at forecast volume |  | 4580
Finance's own model puts the forecast saving nearer $4,900 a month. It assumes the worker and cache tiers grow more slowly than posting volume; this sheet holds them flat, which is the cautious reading.

## Risk register
Risk register
Score is likelihood multiplied by impact, both on a 1-5 scale. Scoring follows PE-STD-004.
ID | Risk | Likelihood | Impact | Score | Gates cutover | Owner | Mitigation
R-01 | Statement endpoint misses its latency objective | 4 | 3 | 12 | Yes | M. Farouk | Add the covering index; ship in 3.0.5 before cutover
R-02 | Dual-write drift during the cutover window | 3 | 5 | 15 | Yes | A. Reyes | Freeze writes for 90 s, reconcile before opening traffic
R-03 | Foreign-exchange rounding defect returns after 3.0.4 | 2 | 5 | 10 | No | J. Lindqvist | Property-based test in CI across 10 million generated cases
R-04 | Rollback exceeds the 30-minute recovery objective | 3 | 5 | 15 | Yes | A. Reyes | Rehearse twice; keep v2.7 warm for 14 days
R-05 | On-call rotation unfamiliar with the new runbook | 4 | 2 | 8 | No | S. Okafor | Two game days completed before cutover
R-06 | Cold-read regression bites under a cache flush | 3 | 3 | 9 | No | M. Farouk | Pre-warm the cache; roll out in 5% stages
Highest score |  | 15
Risks that gate the cutover |  | 3
Gate threshold |  | 12

## Readiness
Operational readiness
The checklist as it stood on 21 August 2026. Status is a dropdown; the counts below follow it.
Area | Owner | Status | Evidence
Runbooks rewritten | S. Okafor | Complete | PE-DOC-311, reviewed 4 August
Dashboards and alerts | M. Farouk | Complete | 18 panels, 11 alert rules
Rollback rehearsal | A. Reyes | Not started | Blocker B-2
Game days (2 required) | S. Okafor | In progress | 1 of 2 done — blocker B-3
Backup and restore drill | J. Lindqvist | Complete | Restored 412M rows in 24 minutes
Capacity headroom of 40% or more | M. Farouk | Complete | Measured 61% at peak
Items on the checklist |  | 6
Complete |  | 4
In progress |  | 1
Not started |  | 1
Share complete |  | 66.67%
The two open items are blockers B-2 and B-3. Both have a named owner and a dated exit; see the risk register and section 6 of the report.